## Sheet1
Step	Task	Partial Tasks	SUM	Time estimated (Prio 1)	Time estimated (Prio below 1)
Grobanalyse-Modell
	Use Cases			1
		Identify and model use cases, Define scenarios and test the use cases
OO-Synthese
	Packaging, Business Classes, Interface, Inheritance, DB Structure, Scenarios		4
		Create packages, package diagram. )GUI and Engine must be strictly separated. Also all code that is not part of this diploma work, be it publicly available open source or from the customer, goes into separate packages))		0.5
		Create buisness classes, Class diagram		1
		Create interfaces and inheritance structure		0.5
		Create logical database model		0.5
		Create sequence diagram for a position estimate from each position provider, Create activity diagram if necessary		1
		Specify test cases and test the model with the scenarios		0.5
Design
	Transfer Business into Design classes, in code		2.5
		Model Business classes into Design classes, apply OO design patterns, Design associations, attributes, methods, enumerations		0.5
		Design the interfaces, Design the packaging		0.5
		Design the database tables		0.5
		Study .NET Unit testing and define test cases (if enough time available)		1
Implementation
	System Interfaces
		Find suitable NMEA lib, Implement outputter, copy data from current estimate into the NMEA classes		1
	User Interfaces		4
		Languages, Designing the Main parts of the dialog		0.5
		Design the WCF classes for Event firing and track segment number input		1
		repopulate event markers		0.5
		Event firing		1
		Implement status providing and GUI Elements, WCF for this.		1
	Hardware Interfaces
		Install adapter, test output with a prototype		0.5
	Start and Shutdown
		Create starter EXE, probably a Windows service for the engine, Create Starter EXE for the GUI		0.5

	Using WiFi		5
		Test Placelab		1
		Get Data		1
		Integrate Placelab		3
	Using GPS
		Integrate GPS		1
	Using IMS		2.5
		Get acquainted with the sensor and the data access		1
		Create position estimates with correct CEP from the data.		0.5
		Design and implement a simple algorithm that links the last known position with the IMS output. (Some sort of back-calculating the acceleration and turnrate error)		1
	Using the track db
		Create track db proxy or list that hold current track waypoints (Probably narrowed down by user input). Calculate nearest point algorithm		1.5
	Using event markers
		Create corresponding position provider		0.5
	Logging (and Emulation)
		Create logger, reading from logs, emulating sensor		1
	Estimating the position
		Create blender		1
Testing
		Accurracy determination			1
		Each requirement implementation by ID, with supervisor			1

Documentation
		Quickstart Guide		0.5
		Finishing doc		1
		Prepare Presentation		0.5