## Sheet1
Preproject
Date	Task description	Time (hours)	Project part ID
11.08.08	Studying MS Project, Creating Pre-Project plan	2.5	Management
12.08.08	Creating Document Templates	3	Documentation
12.08.08	Documenting WLAN Testdrive on train	2	Documentation
28.08.08	WLAN and GPS feasibility measurement	3	Work
09.09.08	Getting positioning data about Swisscom Hotspots in Stations	2	Work
18.09.08	Analysation of available track data of swiss railways	3	Work
20.09.08	Evaluating GPS Hard- and Software	2	Work
29.09.08	Evaluating Inertial hardware	8	Work
30.09.08	Discussing Power consumption, ordering Hardware	2	Work
30.09.08	Evaluating Inertial hardware	1	Work
01.10.08	Discussing Existing Inertial system with PCH	1.5	Work
01.10.08	Discussing existing Post Processing with Michele	0.5	Work
01.10.08	Ordering ublox GPS Hardware	0.5	Work
01.10.08	Documenting Inertial systems	2	Documentation
02.10.08	Evaluating more inertial systems and prices	2	Work
03.10.08	Evaluating more inertial systems and prices	2	Work
06.10.08	Finishing Dok of feasibility study	8	Documentation
09.10.08	Evaluating Inertial hardware	4	Work
14.10.08	Research about AHRS and Kalman	2	Work
03.11.08	Research with Honeywell's magnetic products	2	Work

SRS
20.09.08	Writing parts of the SRS	2	Work
03.10.08	Analysation of the current solution	6	Work
13.10.08	Description of current and new solution	8.5	Work
17.10.08	Mindmap of SRS	1	Work
20.10.08	Writing the SRS, Section 1 and 2	8	Work
21.10.08	Writing SRS part 3	10	Work
22.10.08	Fixing SRS	1.5	Work
24.10.08	CR's from supervisor	1	Work
27.10.08	Time Schedule MS Project	7.5	Management

Diploma Work
12.08.08	Studing existing WLAN solutions	3	Research
12.11.08	Design of the Thesis Presentation, noting Guidelines	1	Documentation
09.10.08	Kick-Off Meeting	3	Management
15.10.08	Designing Data flow for phase 1 and 2	2	Work
17.10.08	Icon design	1	Work
25.10.08	Evaluating Placelab	1	Research
28.10.08	Evaluating Placelab	0.5	Research
28.10.08	Fiddling Comport with Placelab	2	Research

	SUMME	112